## Gantt Chart Template
| Study Phase | [29 empty] | Data pre-processing Phase | [14 empty] | Object Detection Implementation | [34 empty] | Optional Tasks | [14 empty] | Results and Documentation
TASK TITLE | 2022-01-03 |  |  |  |  | 2022-01-10 |  |  |  |  | 2022-01-17 |  |  |  |  | 2022-01-24 |  |  |  |  | 2022-01-31 |  |  |  |  | 2022-02-07 |  |  |  |  | 2022-02-14 |  |  |  |  | 2022-02-21 |  |  |  |  | 2022-02-28 |  |  |  |  | 2022-03-07 |  |  |  |  | 2022-03-14 |  |  |  |  | 2022-03-21 |  |  |  |  | 2022-03-28 |  |  |  |  | 2022-04-04 |  |  |  |  | 2022-04-11 |  |  |  |  | 2022-04-18 |  |  |  |  | 2022-04-25 |  |  |  |  | 2022-05-02 |  |  |  |  | 2022-05-09 |  |  |  |  | 2022-05-16 |  |  |  |  | 2022-05-23 |  |  |  |  | 2022-05-30 |  |  |  |  | 2022-06-06
| M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Study and research
Study Deep Learning | bar: 2022-01-03 M to 2022-01-24 F; 2022-05-09 M to 2022-05-09 F
Research and technical study | bar: 2022-01-17 M to 2022-01-31 F; 2022-05-09 M to 2022-05-09 F
Study Datasets | bar: 2022-01-24 M to 2022-01-31 F; 2022-05-09 M to 2022-05-09 F
Study Kaggle Competition | bar: 2022-01-24 M to 2022-02-14 F; 2022-05-09 M to 2022-05-09 F
Data pre/processing
Image data recollecting and pre/processing | bar: 2022-02-14 M to 2022-03-07 F; 2022-05-09 M to 2022-05-09 F
Object Detection Implementation
Definition of the architecture | bar: 2022-03-07 M to 2022-03-28 F; 2022-05-09 M to 2022-05-09 F
Training of the model | bar: 2022-03-28 M to 2022-04-18 F; 2022-05-09 M to 2022-05-09 F
Evaluation | bar: 2022-03-28 M to 2022-04-18 F; 2022-05-09 M to 2022-05-09 F
Optional Tasks
Semantic Segmentation Implementation | bar: 2022-04-18 M to 2022-05-09 F
Get extra info from detected species | bar: 2022-05-02 M to 2022-05-09 F
Create new Dataset | bar: 2022-05-02 M to 2022-05-09 F
Results and documentation
Comparison of models and conclusion | bar: 2022-05-09 M to 2022-05-16 F
Write documentation and Presentation | bar: 2022-05-09 M to 2022-06-06 W
Study and Research
Data Preprocessing
Object Detection Implementation
Optional Tasks
Results and Documentation
[46 empty] | 2022-01-03 | [11 empty] | 2022-02-14 | [5 empty] | 2022-03-07 | [13 empty] | 2022-04-25 | [5 empty] | 2022-05-16 | [7 empty] | 2022-06-09
[48 empty] | PEC2 | [17 empty] | PEC3 | [17 empty] | PEC4 | [7 empty] | PEC5